|  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **WORKPLAN TEMPLATE** | | | | | | | | |  |
|  |
|  |  |  |  |  |  |  |  |  |  |
| Planning Phase | | | | | | |  |  |  |
| Milestone | Activities | Month (s) | Lead Staff | Support Staff/ Stakeholders | Outputs | Check When Complete |  | Potential Milestones to Consider: |  |
| Example: Innovative tool finalized | Secure vendor | 1 | Staff A | Vendor | Vendor contract |  |  | Innovative tool finalized |  |
| Meet with vendor to discuss custom tool adaptations | 1 | Staff A | Vendor; Staff B | Meeting notes |  |  | Staff training materials and protocols developed |  |
| Make adaptations to tool | 2 | Staff A | Vendor | Initial tool |  |  | All staff trained |  |
| Recruit 10 WIC client testers | 2 | Staff B | Staff A | List of testers |  |  | Client training materials and protocols developed |  |
| Test tool adaptations | 2 | Staff A | Vendor; Staff B; 10 WIC clients | Feedback report |  |  | All clients trained |  |
| Refine tool based on feedback | 3 | Staff A | Vendor | Final tool |  |  | Evaluation plan and manual of procedures completed |  |
|  |  |  |  |  |  |  |  | Survey instrument developed |  |
|  |  |  |  |  |  |  | Interview guide developed |  |
|  |  |  |  |  |  |  | 70% clients downloaded the App |  |
|  |  |  |  |  |  |  | Protocols implemented in clinics |  |
|  |  |  |  |  |  |  | Tool implemented in clinics |  |
|  |  |  |  |  |  |  | Customer satisfaction survey data collected |  |
|  |  |  |  |  |  |  |  | Customer satisfaction interview data collected |  |
|  |  |  |  |  |  |  | Staff satisfaction data collected |  |
|  |  |  |  |  |  |  | Customer satisfaction data analyzed |  |
|  |  |  |  |  |  |  | Tool analytics obtained from vendor |  |
|  |  |  |  |  |  |  | Staff satisfaction data analyzed |  |
|  |  |  |  |  |  |  | Project results shared with Agency |  |
|  |  |  |  |  |  |  |  | Project results disseminated more broadly |  |
|  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |
| Implementation Phase | | | | | | |  |  |  |
| Milestone | Activities | Month (s) | Lead Staff | Support Staff/ Stakeholders | Outputs | Check When Complete |  |  |  |
|  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |
| Evaluation Phase | | | | | | |  |  |  |
| Milestone | Activities | Month (s) | Lead Staff | Support Staff/ Stakeholders | Outputs | Check When Complete |  |  |  |
|  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |